## Situation & Numbers
Business Transformation: Vegetarian Tiffin → Deliveroo & Uber Eats
Client: home kitchen, 30 orders/day, WhatsApp-only · Analyst: Vaishnavi Bhor
Current Daily Orders | Weighted AOV | Annual Revenue (est.) | Gross Margin (direct) | Platform Commission | Setup Cost (one-off) | Revenue Potential | Days to Register Food Business
30 | £7.33 | £57K | 60% | 30% | £1,215 | £130K+ | 28
WhatsApp only | Current menu mix | 260 trading days | Pre-platform | Deliveroo (typical) | To go live on platforms | At 100 orders/day | Minimum by law — start today
SITUATION — WHAT EXISTS TODAY AND WHAT NEEDS TO CHANGE
The operation | 30 vegetarian tiffin orders per day. Menu changes daily. Strong loyal customer base built on WhatsApp. Quality appears strong — the business has retained customers without any marketing.
The problem | Entirely dependent on WhatsApp for orders, discovery, and payment. Cannot scale beyond personal network. No digital presence, no food business registration, no platform listings.
The opportunity | Deliveroo and Uber Eats provide immediate access to thousands of local customers who have never heard of this kitchen. Vegetarian-only is a clear niche — easier to position and discover on platform search.
The constraint | Platform listing requires: (1) food business registration with local authority, (2) a Food Hygiene Rating, (3) standardised fixed menu with allergens, (4) product photos. None of these are currently in place.
What this project delivers | End-to-end transformation roadmap: current state economics → platform pricing model → menu standardisation → compliance checklist → 90-day phased implementation plan.
ANALYTICAL FRAMEWORK — 5 WORKSTREAMS
Workstream | Name | Core Question | Deliverable
WS1 | Current State Economics | What does the business look like today? Revenue, margin, capacity. | Sheet: Platform Pricing
WS2 | Platform Economics & Pricing | Do current prices survive 30% commission? What must platform prices be? | Sheet: Platform Pricing
WS3 | Menu Standardisation | How to transform a daily WhatsApp menu into a permanent platform-ready listing. | Sheet: Standardised Menu
WS4 | Compliance & Legal Setup | What does UK law require before any food business lists on a platform? | Sheet: Compliance
WS5 | 90-Day Implementation Roadmap | Phased plan: week-by-week, cost, owner, dependency. | Sheet: Roadmap

## Platform Pricing
WS2: Platform Economics & Pricing Strategy
Current WhatsApp prices cannot go onto platforms unchanged · 30% commission requires ~30% price uplift
THE CORE PROBLEM — WHY CURRENT PRICES DON'T WORK ON PLATFORM
A £7 WhatsApp order on Deliveroo at 30% commission: Deliveroo takes £2.10. Restaurant receives £4.90. After food + packaging cost (40% of AOV = £2.80), gross profit is £2.10 — a 30% margin. That is marginally viable, BUT: (1) the customer also pays a £2.99 Deliveroo service fee on top, making the real customer cost £9.99. At that customer price point, a £7 restaurant price looks cheap and attracts value expectations that are hard to manage. (2) The right approach is to price the platform menu at £9-10 and maintain a comparable gross margin to the direct channel.
UNIT ECONOMICS: EACH MENU ITEM × EACH CHANNEL
Menu Item | WhatsApp Price | Platform Price (+30%) | Deliveroo Commission (30%) | Restaurant Receives | Ingredient COGS (40%) | Gross Profit | Gross Margin
Tiffin Combo Regular | 7 | 9.49 | 2.847 | 6.643 | 2.8 | 3.843 | 40.5%
Tiffin Combo Large | 7 | 10.49 | 3.147 | 7.343 | 2.8 | 4.543 | 43.31%
Paneer Bhurji Solo (Large) | 8 | 10.99 | 3.297 | 7.693 | 3.2 | 4.493 | 40.88%
Masoor Dal Solo (Large) | 7 | 9.99 | 2.997 | 6.993 | 2.8 | 4.193 | 41.97%
Family Sharing Box | 14 | 17.99 | 5.397 | 12.593 | 5.6 | 6.993 | 38.87%
Today's Special | 6 | 8.49 | 2.547 | 5.943 | 2.4 | 3.543 | 41.73%
CHANNEL COMPARISON — WHAT THE RESTAURANT KEEPS ON A £7 EQUIVALENT SALE
Channel | Customer Pays | Restaurant Receives | COGS | Gross Profit | Gross Margin | Notes
WhatsApp (direct) | £7.00 + self-delivery | 7 | 2.8 | 4.2 | 60% | No commission. Best margin. Limited reach.
Deliveroo (30%) | £9.00 + £2.99 svc fee | 6.3 | 2.8 | 3.5 | 39% | Use for discovery. Price 30% above WhatsApp.
Uber Eats Standard (25%) | £9.00 + svc fee | 6.75 | 2.8 | 3.95 | 44% | Better margin than Deliveroo. Good starting point.
Own Website (Stripe 3%) | £7.70 (10% above direct) | 7.47 | 2.8 | 4.67 | 61% | Best long-term channel. Lower commission. Own data.

## Standardised Menu
WS3: Standardised Platform Menu — WhatsApp Menu → Platform-Ready Listing
Platforms require: fixed permanent items · gram weights · allergen info (LEGAL) · product photos
WHY THE CURRENT MENU CANNOT GO ON DELIVEROO/UBER EATS AS-IS
Problem | Detail | Severity
Daily changing menu | Platforms need a permanent listing. You cannot update your full menu every day. A rotating 'Today's Special' slot is the right solution for daily variety. | BLOCKING
No allergen information | UK law requires allergen info for all 14 allergens on every menu item sold for delivery. Deliveroo will not list you without this. Failing to provide it is a criminal offence. | LEGAL — BLOCKING
No gram weights or portion clarity | 'Medium' and 'Large' mean nothing to a new customer who has never ordered before. Platform listings need: '250g basmati rice', '2 chapatis'. | CONVERSION — BLOCKING
No product photos | Restaurants with photos get 40%+ more clicks on Deliveroo and Uber Eats (both platforms publish this data). A listing without photos will not convert. | CONVERSION — CRITICAL
8 options per day | Too many choices cause decision paralysis. Best practice for a small kitchen: 5-6 permanent items + 1 daily special. Reduces kitchen complexity too. | OPERATIONAL
RECOMMENDED PLATFORM MENU — 6 PERMANENT ITEMS
Item | Platform Description | WhatsApp Price | Platform Price | Portion Size | Allergens (14-allergen check) | Photo Priority | Est. Orders/Day
Tiffin Combo (Regular) | Paneer Bhurji or Masoor Dal + Basmati Rice (250g) + 3 Chapatis. Home-style North Indian vegetarian, freshly made daily. | 7 | 9.49 | ~500g | Gluten (chapati), Dairy (paneer). May contain nuts. | HIGH | 12
Tiffin Combo (Large) | Paneer Bhurji or Masoor Dal + Basmati Rice (350g) + 4 Chapatis. Bigger appetite? This is the one. | 7 | 10.49 | ~700g | Gluten (chapati), Dairy (paneer). May contain nuts. | HIGH | 8
Paneer Bhurji (Solo, Large) | Rich Paneer Peas Bhurji in tomato-onion masala. With 4 chapatis OR large basmati rice — choose at checkout. | 8 | 10.99 | ~400g | Dairy (paneer), Gluten if chapati. May contain nuts. | HIGH | 4
Masoor Dal (Solo, Large) | Red lentil dal with whole spices, cooked slow. With 4 chapatis OR large basmati rice — choose at checkout. Fully vegan without chapati. | 7 | 9.99 | ~400g | Gluten if chapati selected. Vegan option available. May contain nuts. | HIGH | 3
Family Sharing Box | Large Bhurji + Large Masoor + 6 chapatis + large rice. Feeds 2-3 people. The full home-cooked meal. | 14 | 17.99 | ~1.2kg | Gluten (chapati), Dairy (paneer). May contain nuts. | HIGH | 2
Today's Special | Ask us what's cooking! Daily rotating dish — seasonal vegetables, extra curries, or festive specials. Allergens listed daily in description. | 6 | 8.49 | Varies | Listed daily — check item description. | LOW | 1

## Compliance Checklist
WS4: UK Compliance & Legal Setup — Complete Before Going Live
Sources: FSA (food.gov.uk) · GOV.UK · Deliveroo (Delta Digital 2025) · Uber Eats (Deliverect 2025)
THE LEGAL PICTURE — WHAT UK LAW REQUIRES OF A HOME FOOD BUSINESS
Legal Item | What It Means in Practice
Who this applies to | Any UK business that regularly supplies food to the public — even from a home kitchen. 'Regularly and organised basis' = you are a food business. WhatsApp tiffin orders = food business.
Registration | FREE and mandatory. Must be done at least 28 days before trading (or immediately if already trading). Cannot be refused. Apply via your local council website.
Food hygiene certificate | Not compulsory but FSA strongly recommends it. Level 2 Food Safety for Catering. Online course, ~£25, one day. Deliveroo/Uber Eats may require it.
HMRC self-employment | Required — even if part-time. Register at gov.uk/register-for-self-assessment. Tax on profits above personal allowance.
Allergen law | UK Food Information for Consumers Regulation. 14 allergens must be declared on every dish sold for delivery. Failure = criminal offence. Dairy and gluten both present in this menu.
Food Hygiene Rating Scheme | Inspected by Environmental Health after registration. Ratings 0-5. Deliveroo requires minimum rating to list. Aim for 5 — all businesses should be able to achieve this.
FULL COMPLIANCE & SETUP CHECKLIST — TICK BEFORE GOING LIVE
Item | Category | Cost (£) | Timeline | Status | Action Required | Source
Register food business with local authority | LEGAL | 0 | 28 days before trading | ⬜ TODO | Go to local council website now — search '[your council] food business registration' | FSA / GOV.UK
Register as self-employed with HMRC | LEGAL | 0 | Before trading | ⬜ TODO | gov.uk/register-for-self-assessment | GOV.UK / HMRC
Level 2 Food Hygiene Certificate (online) | LEGAL | 25 | 1 day (online) | ⬜ TODO | highspeedtraining.co.uk or similar — ~£25 | FSA guidance
Document allergens for all 6 menu items | LEGAL | 0 | Immediate | ⬜ TODO | Use FSA allergen checker tool. List all 14 allergens per item. | UK FIC Regulation
HACCP-lite food safety system | LEGAL | 0 | 1-2 days | ⬜ TODO | Download FSA 'Safer Food Better Business' pack — free | FSA
Public liability insurance | RECOMMENDED | 150 | 1-2 days | ⬜ TODO | Compare on Simply Business or PolicyBee — ~£150/yr | Industry standard
Food-grade packaging with allergen labelling | LEGAL | 100 | Before go-live | ⬜ TODO | Labels must include: business name, allergens, storage instructions | UK food labelling law
Environmental Health kitchen inspection | LEGAL | 0 | Council arranges post-registration | ⬜ AUTO | Happens automatically after registration — make kitchen inspection-ready | FSA
5-star Food Hygiene Rating | PLATFORM | 0 | At inspection | ⬜ TODO | Clean and document everything. Use FSA checklist to self-audit first. | FHRS
Deliveroo listing application | PLATFORM | 510 | After 5-star rating | ⬜ TODO | Apply at restaurants.deliveroo.com — £510 onboarding fee (8 instalments) | Delta Digital 2025
Uber Eats listing application | PLATFORM | 0 | After food hygiene cert | ⬜ TODO | Apply at merchants.ubereats.com — faster onboarding than Deliveroo | Deliverect 2025
Product photography (6 menu items) | PLATFORM | 200 | 1 day shoot | ⬜ TODO | Hire local food photographer OR use Deliveroo's in-house photo service | Platform conversion data
Google Business Profile setup | RECOMMENDED | 0 | 2 hours | ⬜ TODO | business.google.com — free, drives local organic discovery | Industry standard
Simple website with menu + ordering link | RECOMMENDED | 200 | 1-2 weeks | ⬜ TODO | Squarespace or Wix — £15/month. Embed Uber Eats/Deliveroo order link. | Recommended
Instagram page with food photos | RECOMMENDED | 0 | 1-2 hours | ⬜ TODO | Username = business name. Link in bio to delivery platform. | Industry standard
TOTAL SETUP COST |  | 1185

## 90-Day Roadmap
WS5: 90-Day Implementation Roadmap — Phase by Phase
Phase 1: Legal foundation (Weeks 1-4) · Phase 2: Platform launch (Weeks 5-8) · Phase 3: Scale (Weeks 8-12)
PHASE 1 — LEGAL FOUNDATION (WEEKS 1–4): DO NOT SKIP THIS
⚠ CRITICAL: The food business registration takes 28 days minimum before you can legally trade. Start this on Day 1, regardless of anything else. Everything else in this roadmap depends on it.
Week | Task | Owner | Cost | Dependency | Why This Week
Week 1 | Register food business with local council (online, 10 minutes) | Founder | £0 | None — do today | 28-day clock starts now. Everything is blocked until this is done.
Week 1 | Register as self-employed with HMRC (online, 20 minutes) | Founder | £0 | None | Tax compliance — HMRC tracks Deliveroo/Uber Eats income from Jan 2024.
Week 1 | Complete Level 2 Food Hygiene Certificate online (1 day) | Founder | £25 | None | Required for inspection, platforms prefer it. Cheap and fast.
Week 1-2 | Document allergens for all 6 standardised menu items | Founder | £0 | Menu finalised | LEGAL REQUIREMENT. Use FSA allergen checker. Keep written records.
Week 2 | Download and complete FSA 'Safer Food Better Business' pack | Founder | £0 | Food hygiene cert | Written food safety system = council will want to see this at inspection.
Week 2-3 | Finalise standardised 6-item menu with descriptions and gram weights | Founder | £0 | None | Platform needs fixed menu to submit listing application.
Week 3 | Purchase public liability insurance | Founder | £150 | Business registered | Protects against delivery-related claims. Required before operating at scale.
Week 3-4 | Source food-grade packaging with allergen/business name labels | Founder | £100 | Menu finalised | Legal requirement for delivery orders. Order in bulk — cost per unit drops.
PHASE 2 — PLATFORM LAUNCH (WEEKS 5–8)
Week | Task | Owner | Cost | Dependency | Why This Week
Week 4-5 | Environmental Health kitchen inspection (council arranges) | Council | £0 | Registration complete | If kitchen is clean and documented — aim for 5 stars immediately.
Week 5 | Professional food photography (6 items + setup shot) | Photographer | £200 | Menu finalised | 40%+ conversion uplift. Non-negotiable for platform listings. Book in advance.
Week 5-6 | Apply to Uber Eats — upload menu, photos, pricing | Founder | £0 | 5-star rating + photos | Faster onboarding than Deliveroo. Start here. Go live quickly.
Week 5-6 | Apply to Deliveroo — upload menu, photos, pricing | Founder | £510 | 5-star rating + photos | £510 spread over 8 payment deductions from earnings. Larger audience.
Week 6 | Set pricing 30% above WhatsApp prices on both platforms | Founder | £0 | Platform accounts live | Standard industry practice. Absorbs commission. Keeps margin comparable.
Week 6-7 | Build simple website: Squarespace or Wix with order links | Founder | £200 | None — run in parallel | Own digital presence = not fully dependent on platform algorithms.
Week 7 | Set up Google Business profile with photos and menu | Founder | £0 | Website live | Free local search visibility. Customers search 'vegetarian food delivery [area]'.
Week 7-8 | Soft launch: tell WhatsApp customers about Deliveroo listing, ask for reviews | Founder | £0 | Platform listing live | First 10 reviews are critical for platform algorithm placement.
PHASE 3 — SCALE (WEEKS 9–12)
Week | Task | Owner | Cost | Dependency | Focus
Week 8-10 | Monitor platform: acceptance rate, avg rating, prep time compliance | Founder | £0 | Both platforms live | Low acceptance rate or slow prep = platform penalises your visibility.
Week 9-10 | Add 'Today's Special' as a rotating daily item on platform | Founder | £0 | Base menu stable | Brings back repeat customers. Easy to manage once workflow is set.
Week 10-11 | Instagram: post 3x/week — food photos, daily special, behind-scenes | Founder | £0 | Photos available | Vegetarian food photographs well. Build following before paid ads.
Week 11-12 | Review P&L: direct vs platform channel split. Adjust if needed | Founder | £0 | Full month of platform data | Data from first full month: which platform performs, which items sell.
Week 12 | Assess kitchen capacity for 75-100 order target. Plan next hire if needed | Founder | £0 | Volume trending up | At 75+ orders/day, solo operation becomes difficult. Plan ahead.

## Recommendations
Key Recommendations & Honest Assessment
What to do, in what order, and what to expect — honestly
THE FIVE THINGS THAT MATTER MOST
Priority | Recommendation | Timing
1 — LEGAL FIRST | Register as a food business TODAY. The 28-day waiting period before trading is non-negotiable. If you are already trading without registration, this is urgent. Everything else in this plan cannot happen until registration is complete and you have a Food Hygiene Rating. | URGENT — do today
2 — REPRICE FOR PLATFORMS | Your current £6-8 menu cannot go on Deliveroo/Uber Eats unchanged. At 30% commission, a £7 item leaves only 30% gross margin — workable, but the customer also pays £2.99 service fee, making their real cost £9.99. Price transparently: set platform prices at £9-10. This is standard industry practice and no customer will complain if the quality is there. | Price before listing
3 — FIX THE MENU BEFORE APPLYING | Deliveroo and Uber Eats applications require allergen information for every item. You need a standardised, permanent menu with descriptions, gram weights, and allergen declarations. Consolidate from 8 daily options to 6 permanent items plus one daily special. This simplifies your kitchen workflow too. | Before platform apply
4 — PHOTOGRAPHS ARE NON-NEGOTIABLE | Both platforms publish data showing that listings with professional food photos receive 40%+ more clicks. A £200 food photography session (6 items) is the highest-ROI spend in this entire plan. Without photos, your listing will not convert — it will just sit there. | Budget £200 for this
5 — THINK HYBRID FROM DAY ONE | Do not become 100% dependent on Deliveroo/Uber Eats. They take 30% of every order. Your loyal WhatsApp customers should eventually order via your own website (3% Stripe fee). Use the platforms for discovery — they are your marketing channel, not your business model. Build your own customer list from day one. | Long-term strategy
HONEST ASSESSMENT — WHAT IS REALISTIC
Area | Honest Assessment
Revenue projection | At 100 orders/day (50 WhatsApp + 50 platform), after commission: ~£130K annual net revenue vs ~£57K today. This assumes the platforms perform — it is not guaranteed. In the first 3 months, expect lower volumes as the listing builds reviews and algorithm placement.
The platform algorithm | Both Deliveroo and Uber Eats prioritise restaurants with: high acceptance rate (>95%), fast prep time, high rating (>4.5 stars), and good review volume. In the first 30 days, your placement will be low. This improves with volume and ratings. Mobilising WhatsApp customers to leave Deliveroo reviews immediately is critical.
Kitchen capacity | At 30 orders/day, one person can manage. At 75+ orders/day with platform volume, the timing pressure increases significantly — platform orders arrive in clusters and have defined prep time expectations. Plan your kitchen workflow before hitting this volume, not after.
Deliveroo vs Uber Eats | Start with Uber Eats first — no onboarding fee, faster approval, good volume. Add Deliveroo after 4-6 weeks — larger UK audience, but the £510 onboarding cost and slower process make it a second step.
What could go wrong | Poor Food Hygiene Rating (below 3) = cannot list. Low review score = platform suppresses your listing. Slow prep times = orders cancelled and rating drops. HMRC reporting = your Deliveroo/Uber Eats income is automatically reported to HMRC from 2024. Declare it.
Vaishnavi Bhor · MSc Business Analytics, University of Manchester · vbhor207@gmail.com · linkedin.com/in/vaishnavi-bhor-business-analyst · vbho.github.io/portfolio